## Sheet1
[5 empty] | Program of Works Example | [5 empty] | Program of Works Example | [6 empty] | Program of Works Example
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preliminary's | Preliminary's | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon | Week Starting Mon
Input Start Date |  |  |  | 2009-09-01 | 2009-09-08 | 2009-09-15 | 2009-09-22 | 2009-09-29 | 2009-10-06 | 2009-10-13 | 2009-10-20 | 2009-10-27 | 2009-11-03 | 2009-11-10 | 2009-11-17 | 2009-11-24 | 2009-12-01 | 2009-12-08 | 2009-12-15 | 2009-12-22 | 2009-12-29 | 2010-01-05 | 2010-01-12 | 2010-01-19
|  |  |  | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
|  |  |  | Materials Delivered | Pour Concrete #2 | [5 empty] | Fit Ridge Beam | NHBC&REGS Inspected Roof | Fit Facia Boards | Fit Slates to Rear Roof | Fan Holes Cut | Order Plasterboards | Elec& Plumb finish 1st fix |  |  |  | Tiling
|  | NHBC notification | F10 submission | 1st Conc pour | Bricky's | Bricky's |  | Scaffold Start | 2nd lift, Lintol hight | Lintols | Roof Structure Started | Fit Roof insulation | Fire stops (Party wall) | Fit Down Pipes | Plumb 1st fix | Fit Plumbing Tails | Plaster boards Del | Ceiling Plaster Skim | Fit Wall Plaster Boards | Plaster boarding snags | Elec & Plumbing 2nd | Appliances | Decorating snags | Viewings
|  |  | CDM consultation | Shuttering | Foundation Blocks | Start from DPC |  | 1st lift, Window sills |  | 4th lift, | Fit Roof Restraint Straps | dormer boarding | Fit Barge Boards | Fit soil & Vent Pipes | Fit Flooring (Both Flrs) | Fit Floor Insulation | PlasterBoard Ceilings |  | Gas/Water/Elec/BT | Fit Internal Doors | Fit Baths/Showers cub | Fixtures & Fittings | Landscaping Completed
|  | Architect consultations | Engineer consultations | Start Steel Fixing | brickwork to DPC | Start Blockwork | Fit Grnd Floor Joist/Beams | Trestle Hight internal | Fit Padstones | Brickwork | Fit Cut ups Cav Closers | Fit Roof Boarding | Order Floor Insulation Bats | Fit Slates to Front Roof |  | Fit Internal stud work | Glass Delivery | Path Materials Delivery | Joinery 2nd fix | Decorating | WC/sinks fitted | Fit/Test Boiler | Fit Curtain rails
|  | Drawings | Appoint NHBC | Reinforcement | Commons Delivery | Start Stonework | Block Infilling | Fit Service Boxes | Fit Lintols |  | Set Purlins if any | Valley's constructed | Heating pipes B.Boxs | Elec Materials Delivered | Fit initial Pipe runs | Fit Door Frames | Fit Window Frames | Fit Glazing | Order Garage Door | Fit Skirts/Architraves | Radiators mounted | Tiling Completed | Footpaths finished
Attached House |  | Order Stone/Blocks etc | Spoil removal | (Cages) | Sand/Cement Del |  | Temporary Flr Boards | Fit Hockey Stick | Fit 1st Floor Joist | Fit 1st floor Restraint straps | Underside netting | Fit Soil roof vents | Tile or slate dormers | Elec first fix | Fit Drainage outlets | Patios Delivered |  | Garage Construction | Book Painters | Lay Rear Paths | Fit lights/switches/Soc | Fit Taps,toilet seats | Fit Garden Fences
Program Schedule |  | Order Dec Cills/Lintols | Tree removal | Extra Shuttering | Wall ties Delivery | Fit DPC Membrane | Fit Door Templates | Fit Decorative Sills | Internal wall build | Block Infilling | Purlin Positions if any | Inspections | Fit Chimney Vent | Fit initial Cable runs | Stairs Delivery | Window Frames del | Fit Stairs | Order Skirts/Architrave | Wall Plasterboard SkIm | Order Tiling | Fit Worktops | Garage Doors Fitted | Cleaning
|  | Order Steel Mesh & Bar | Shuttering | Order Service Boxes | Book Scaffold | Oversite Concrete | Fit Wall Insulation | Fit Window Templates | Inspections | restraint straps | Fit Rafters in place |  | Fit Rainware |  | Fit Alarm Cables/Video/TV | Noggs for Pendants | Fit Glazing | Mark out Drive/paths | Landscape Rear | Fit Kitchen Units | Fit Door Hardware | Fit Laminate Flooring | Dressing
|  | contact Services | Heave protection | Order Sand/Cement/Febmix | Drainage layout | Radon barrier | Fit Floor Insulation | Mullions? |  | Cavity Closers Delivery | Slates Delivered |  | Aerial fitted | Order Decking for Floors | Fit Door Cav Closers | 1st Paint Windows |  | Clear Base around hs | Inspections | Laminate Delivery | Rear Fences mounted | Heating Tested | Final Checks
|  | Fencing? | Inspections | Order Regularised Joist #1&2 | Order Templates | Insulation Delivery | Inspections DPC |  | 3rd lift, | Roof Materials Del | Drainage Delivery |  | Fit Lat & Felt | Flooring Materials del | Order for Paths etc | Plumb Preasure Test | Boxing Pipework | Fit Window Sills | Skirt/Architrave Delivery |  | Inspections | Electrical Testing complete | Skip for clearance
|  |  | Order kicker blocks | Order Hockey Stick/Box | Soil pipes in place | Order Floor 2 I-Beams |  | Floor Joist Delivery #2 | Order Cavity Closers | Order Patio Doors | Valley sets | Seal all Cavity's |  |  | Order Stud Timber | Order Doors+ Front dr+Frm | Start Access Court Prep | Fit Front Door | Lay Front Paths | WC's/Sinks/Bath Delivery | Turfing Rear
|  | Order drainage | Order Floor I-Beams+Hangers | Order Insulation | Blocks/Stone Delivery | Order Lintols (struc) | Lintols (Struc) Delivery | Order Ridge beam | Order Windows onsite | 5th lift Gables cut ups | Cut up's complete |  | Fit Lead work | Order Stairs | Paint Facias | Order Door Frames | Window Sills Delivery | Footpath Prep | Order WC's/Sinks/Bath | Elec 2nd fix Mat Del. | Garage Doors Delivery |  | Inspections
|  | Excavate for drainage | Mark Out, Check Position | Order Wall Ties | I-beams delivery | Order Ridge Beams | Décor Cills Lintols Del | Order PAN Timber |  | Order Roof Materials | Fit Restraint Straps |  | Order Stairs | Back boxes mounted | Lead work complete |  | Final paint Windows | Landscaping Front | Lay Outdoor Cables for Lighting | Rads Delivered | Boiler Delivery |  | Regs/NHBC Final Inspection
|  | Fit Drainage | for reinforced strip footings | Soil pipes positioned | Radon Protection DPC's |  | Service box Deliivery |  |  | Order Slates | Order Plumbing Mat's |  |  | Fit Soffits (enclosed) | Finish all under floor work | Fit Patio Cav Closers | Remove Scaffold | Order Kitchen | Order Laminate | Turf Delivery | Turfing Front Lawn
|  |  | Excavate Footings | Inspections | [5 empty] | Pan fitted | Velux positioned |  |  |  |  | Fit Patio Doors | Stone Delivery | Order Boiler & RADS | Kitchen Delivery
[16 empty] | Order Sewer & M.Holes pipe | Dropped Curbs Delivery | Order Electrical, Cable, Boxes
[16 empty] | Order Dropped Curbs | Sewer Pipes Materials Del | Water pipes layed | Sewer connection |  | Driveways Started
General | [14 empty] | Garage Prep | Sewerage Connection start |  | Gas Sleaves layed | Services Connected |  | Access Court detail
Site | [16 empty] | Lay Cross Drainage | Electric Sleave layed | Elec/Water/BT/Gas? | Landscaping | Lay Block Paving
Program Schedule | [15 empty] | Sevice trenches dug | Storm trench dug | Bt Sleave Layed | Garden Fence Delivery | Sand Bed | Landscaping
[16 empty] | Inspections | Sewerage trench dug | Inspections | Bndry Fence Delivery | Hardcore Court | Driveways Complete
[16 empty] | Drives and Paths Marked | Sewerage Pipe layed | Services to Detached | Paint Delivered | Whacker Hardcore | Bndry Fence Erection
[17 empty] | Storm pipe layed | Order Turf | Driveway Materials Del | Order Bndry Fence
[17 empty] | Inspections | Order Paving/Drive Materials | Lower Cables in Footpath | Order Garden Fence
[18 empty] | Fit Drop Curbs |  | Order for Paths etc
Gas Application
Sewerage Application
Electric Application
BT Pole, Line Application
Dropped Curb Application
Formulas:
Program of Works Example = [Week Starting Mon]+7
Week Starting Mon = [Program of Works Example]+7
Week Starting Mon = [Week Starting Mon]+7